## CIM
Strenthening and Digitization of Working of Inspectorate of Mines, Punjab, Lahore
Sr# | PC-1 Scope | Sub Scope | Status | Anticipated Delivery | Remarks | Responsibility | Dependencies
1 | Registration and geo tagging of Leases / Mines | Geo-Tagging Mobile App | Completed |  | *mention remarks like 2 meetings done, meeting pending from dept etc.* | Dev and SE | CIM
|  | Geo-Tagging User Registration | Completed |  | *mention remarks like 2 meetings done, meeting pending from dept etc.*
|  | Registration Module For Mine Owners | Completed |  | *mention remarks like 2 meetings done, meeting pending from dept etc.*
|  | User Management Module | Completed |  | *mention remarks like 2 meetings done, meeting pending from dept etc.*
|  | Geo-Tagging Real-Time Reporting | Completed |  | *mention remarks like 2 meetings done, meeting pending from dept etc.*
|  | Overall Analytical Dashboard for Progress Monitoring | Completed |  | *mention remarks like 2 meetings done, meeting pending from dept etc.*
|  | Geo-Tagging App Enhancements with Tehsil Dropdown. | Completed |  | *mention remarks like 2 meetings done, meeting pending from dept etc.*
|  | Geo-Tagging App Enhancements with Mineral Type Dropdown. | Completed |  | *mention remarks like 2 meetings done, meeting pending from dept etc.*
|  | Geo-Tagging App Enhancements with Display of Live Latitude & Longitude | Completed |  | *mention remarks like 2 meetings done, meeting pending from dept etc.*
|  | Geo-Tag Data Validation | *mention status like requirement gathering done, mockups done, mockups approval etc.* | mention the tentative date you think this sub scope (module) will be completed | Pending from Department's End.
|  | Removal of Duplicate & Test Entries | *mention status like requirement gathering done, mockups done, mockups approval etc.* | mention the tentative date you think this sub scope (module) will be completed | *mention remarks like 2 meetings done, meeting pending from dept etc.*
|  | Mines Owner Module Linkage with Inspection Reports | *mention status like requirement gathering done, mockups done, mockups approval etc.* | mention the tentative date you think this sub scope (module) will be completed | Mine Owners Regstration pending from Department's End
|  | Role wise User Manuals in both Web Portal & Mobile App | *mention status like requirement gathering done, mockups done, mockups approval etc.* | mention the tentative date you think this sub scope (module) will be completed | *mention remarks like 2 meetings done, meeting pending from dept etc.*
|  | Customize Reports Share by the Department | *mention status like requirement gathering done, mockups done, mockups approval etc.* | mention the tentative date you think this sub scope (module) will be completed | Pending from Department's End.
|  | Fix reported bugs if any | *mention status like requirement gathering done, mockups done, mockups approval etc.* | mention the tentative date you think this sub scope (module) will be completed | *mention remarks like 2 meetings done, meeting pending from dept etc.*
2 | Mines Inspection Module | CIM Inspection Mobile App | Completed |  | *mention remarks like 2 meetings done, meeting pending from dept etc.*
|  | Violation letter issuance System | Completed |  | *mention remarks like 2 meetings done, meeting pending from dept etc.*
|  | Authority Letter Issuance System | Completed |  | *mention remarks like 2 meetings done, meeting pending from dept etc.*
|  | Prosecution Letter | Completed |  | *mention remarks like 2 meetings done, meeting pending from dept etc.*
|  | Recent Record Uploads and History | Completed |  | *mention remarks like 2 meetings done, meeting pending from dept etc.*
|  | Add QR Code in all PDF letters. | *mention status like requirement gathering done, mockups done, mockups approval etc.* | mention the tentative date you think this sub scope (module) will be completed | *mention remarks like 2 meetings done, meeting pending from dept etc.*
|  | Inspector Digital Signature incorporation in Violation Letter. | Completed |  | *mention remarks like 2 meetings done, meeting pending from dept etc.*
|  | Soft Delete enhancement in entire Software(s) architecture | *mention status like requirement gathering done, mockups done, mockups approval etc.* | mention the tentative date you think this sub scope (module) will be completed | *mention remarks like 2 meetings done, meeting pending from dept etc.*
|  | Inspectors Digital Signature should be in Blue color | Completed |  | *mention remarks like 2 meetings done, meeting pending from dept etc.*
|  | Revamping of the Web portal Design if needed | *mention status like requirement gathering done, mockups done, mockups approval etc.* | mention the tentative date you think this sub scope (module) will be completed | *mention remarks like 2 meetings done, meeting pending from dept etc.*
|  | Fix reported bugs if any | *mention status like requirement gathering done, mockups done, mockups approval etc.* | mention the tentative date you think this sub scope (module) will be completed | Mostly Fixed, but working on sprint wise.
|  | Add at least 5 names empty place holder for prosecution letter | *mention status like requirement gathering done, mockups done, mockups approval etc.* | mention the tentative date you think this sub scope (module) will be completed | Department to remove from some place.
|  | All perfoma(s) list on web portal must have Download as Excel button | *mention status like requirement gathering done, mockups done, mockups approval etc.* | mention the tentative date you think this sub scope (module) will be completed | *mention remarks like 2 meetings done, meeting pending from dept etc.*
3 | Application For Field Officers To digitize the inspection Regime | Inspection Coal Performa | Completed |  | Completed in violation letter , remains in other letters i.e. prosecution letter and authority letter.
|  | Inspection Other Than Coal Performa | Completed |  | *mention remarks like 2 meetings done, meeting pending from dept etc.*
|  | Inspection Laboratory Form | Completed |  | *mention remarks like 2 meetings done, meeting pending from dept etc.*
|  | Rescue Station Inspection Form | Completed |  | *mention remarks like 2 meetings done, meeting pending from dept etc.*
|  | Add Diary No Text Field in All Inspection Mobile App Performa(s) | Completed |  | *mention remarks like 2 meetings done, meeting pending from dept etc.*
|  | Add ‘Request Edit’ option in inspection mobile all perfoma(s). | *mention status like requirement gathering done, mockups done, mockups approval etc.* | mention the tentative date you think this sub scope (module) will be completed | *mention remarks like 2 meetings done, meeting pending from dept etc.*
|  | Fix reported bugs if any. | Completed |  | *mention remarks like 2 meetings done, meeting pending from dept etc.*
4 | Digitization of Payments related to Challan | Implemented as Scan & Upload Mechanism | Completed |  | Payment challan can be upload by inspectors and viewed by CIM against each Performa
|  | Department has halt the E-Payment. At the moment upload image is used. | Completed |  | *mention remarks like 2 meetings done, meeting pending from dept etc.*
5 | Digitization of Permit Manager | Authorization Module | Completed |  | *mention remarks like 2 meetings done, meeting pending from dept etc.*
|  | Renewal Module | Completed |  | *mention remarks like 2 meetings done, meeting pending from dept etc.*
6 | Digitization of Department Legal Framework | Implemented as Scan & Upload Mechanism | Completed |  | *mention remarks like 2 meetings done, meeting pending from dept etc.*
7 | Return Submission System | Production Return Submission System | Completed |  | *mention remarks like 2 meetings done, meeting pending from dept etc.*
8 | Accident and Incident Report Submission Process | Reporting of Fatal Accidents | Completed |  | *mention remarks like 2 meetings done, meeting pending from dept etc.*
9 | Overall Inspectors Grading Module | New Module but DDSC pending | N/A |  | DDSC pending
10 | Inspectors Tour Roaster Module | New Module but DDSC pending | N/A |  | DDSC pending

## Royalty
Digitized Royalty Monitoring of Minerals for the Office of Deputy Director, Chakwal
Sr# | PC-1 Scope | Sub Scope | Status | Anticipated Delivery | Remarks | Responsibility | Dependencies
1 | Integration of Weigh Bridges of large-scale mining industry with Software Application | LSM Cement Plants Web API Endpoint Developmet | Completed | mention the tentative date you think this sub scope (module) will be completed | API Endpoint Development is completed. Pending Integration with Cement Plants. | Dev, SE | DG Office MMD, Cement factories
|  | LSM Cement Plants Web API Dashboard Stats | *mention status like requirement gathering done, mockups done, mockups approval etc.* | mention the tentative date you think this sub scope (module) will be completed | *mention remarks like 2 meetings done, meeting pending from dept etc.* | Dev, SE | DG Office MMD, Cement factories
|  | LSM Cement Plants Web API Reports | *mention status like requirement gathering done, mockups done, mockups approval etc.* | mention the tentative date you think this sub scope (module) will be completed | *mention remarks like 2 meetings done, meeting pending from dept etc.* | Dev, SE | DG Office MMD, Cement factories
2 | Digitize the mechanism for vehicle monitoring in terms of load, no of vehicles enter/exit for small scale and large-scale mines and minerals | Digitization of Royality Challan Slip through Android Application. | *mention status like requirement gathering done, mockups done, mockups approval etc.* | mention the tentative date you think this sub scope (module) will be completed | *mention remarks like 2 meetings done, meeting pending from dept etc.* | Dev, SE, Tech | DG Office MMD, Chakwal DD MMD Office, C&W Department
|  | Verification of Challan Slip via QR Code | *mention status like requirement gathering done, mockups done, mockups approval etc.* | mention the tentative date you think this sub scope (module) will be completed | *mention remarks like 2 meetings done, meeting pending from dept etc.* | Dev, SE, Tech | DG Office MMD, Chakwal DD MMD Office, C&W Department
|  | Artificial Intelligence and Machine Learning for lessee at check post | *mention status like requirement gathering done, mockups done, mockups approval etc.* | mention the tentative date you think this sub scope (module) will be completed | *mention remarks like 2 meetings done, meeting pending from dept etc.* | Dev, SE, Tech | DG Office MMD, Chakwal DD MMD Office, C&W Department
3 | Mobile/web-based Application for tracking of Minerals | Minerals Production Tracking Mobile App | *mention status like requirement gathering done, mockups done, mockups approval etc.* | mention the tentative date you think this sub scope (module) will be completed | *mention remarks like 2 meetings done, meeting pending from dept etc.* | Dev, SE | DG Office MMD
|  | Minerals Production Tracking Web Module | *mention status like requirement gathering done, mockups done, mockups approval etc.* | mention the tentative date you think this sub scope (module) will be completed | *mention remarks like 2 meetings done, meeting pending from dept etc.* | Dev, SE | DG Office MMD
|  | Integration Centralized Web Portal and Dashboard | *mention status like requirement gathering done, mockups done, mockups approval etc.* | mention the tentative date you think this sub scope (module) will be completed | *mention remarks like 2 meetings done, meeting pending from dept etc.* | Dev, SE | DG Office MMD
4 | Establishment of Command and Control Center (CCC) for monitoring of live operations | CCC Room at DG Office | Completed | mention the tentative date you think this sub scope (module) will be completed | *mention remarks like 2 meetings done, meeting pending from dept etc.* | Ops, Tech | DG Office MMD

## DG Office
Strenthening of Directorate General Mines & Minerals Punjab and IT Integration of Administrative Department
Sr# | PC-1 Scope | Sub Scope | Status | Anticipated Delivery | Remarks | Responsibility | Dependencies
1 | Android application for Inspection Module | Minor Mineral Inspection Performa | *mention status like requirement gathering done, mockups done, mockups approval etc.* | mention the tentative date you think this sub scope (module) will be completed | *mention remarks like 2 meetings done, meeting pending from dept etc.* | DEV, SE | DG Office MMD
|  | Small Scale Mining PL Performa | *mention status like requirement gathering done, mockups done, mockups approval etc.* | mention the tentative date you think this sub scope (module) will be completed | *mention remarks like 2 meetings done, meeting pending from dept etc.* | DEV, SE | DG Office MMD
|  | Small Scale Mining ML Performa | *mention status like requirement gathering done, mockups done, mockups approval etc.* | mention the tentative date you think this sub scope (module) will be completed | *mention remarks like 2 meetings done, meeting pending from dept etc.* | DEV, SE | DG Office MMD
|  | Large scale Mining Surface Performa | *mention status like requirement gathering done, mockups done, mockups approval etc.* | mention the tentative date you think this sub scope (module) will be completed | *mention remarks like 2 meetings done, meeting pending from dept etc.* | DEV, SE | DG Office MMD
|  | Large scale Mining Underground Performa | *mention status like requirement gathering done, mockups done, mockups approval etc.* | mention the tentative date you think this sub scope (module) will be completed | *mention remarks like 2 meetings done, meeting pending from dept etc.* | DEV, SE | DG Office MMD
|  | Large scale Mining Inspection report Performa | *mention status like requirement gathering done, mockups done, mockups approval etc.* | mention the tentative date you think this sub scope (module) will be completed | *mention remarks like 2 meetings done, meeting pending from dept etc.* | DEV, SE | DG Office MMD
2 | Online Lease Application | LSM Lease Application | *mention status like requirement gathering done, mockups done, mockups approval etc.* | mention the tentative date you think this sub scope (module) will be completed | *mention remarks like 2 meetings done, meeting pending from dept etc.* | DEV, SE | DG Office MMD
|  | SSM Lease Application | *mention status like requirement gathering done, mockups done, mockups approval etc.* | mention the tentative date you think this sub scope (module) will be completed | *mention remarks like 2 meetings done, meeting pending from dept etc.* | DEV, SE | DG Office MMD
|  | LSM / SSM Application Inspection Report | *mention status like requirement gathering done, mockups done, mockups approval etc.* | mention the tentative date you think this sub scope (module) will be completed | *mention remarks like 2 meetings done, meeting pending from dept etc.* | DEV, SE | DG Office MMD
3 | Integration of Existing and new application at centralized dashboard | Dashboard stats with real time monitoring | *mention status like requirement gathering done, mockups done, mockups approval etc.* | mention the tentative date you think this sub scope (module) will be completed | *mention remarks like 2 meetings done, meeting pending from dept etc.* | DEV, SE | DG Office MMD
4 | Online software configuration for meetings | Zoom licenses | Completed | N/A |  | OPS | DG Office MMD
5 | Complaint Management System | CCC Helpline | Completed | N/A |  | OPS | DG Office MMD and PITB CCC
6 | E-FOAS (Daak management System) |  | Files scanning is being done | End of 2022 | *mention remarks like requirement gathering done, mockups done etc.* | OPS | DG Office and PITB EFOAS Team
7 | Inventory Management System | HRMIS (Human Resource Management Information System) | Data entry is being done | mention the tentative date you think this sub scope (module) will be completed | *mention remarks like requirement gathering done, mockups done etc.* | DEV, SE | DG Office and PITB HRMIS Team
8 | ESS mobile application | New Module (in case PC-1 gets revised) | N/A | N/A |  | SE, OPS | DG Office MMD and PITB ESS Team
9 | Case Management System (CMS) | New Module (in case PC-1 gets revised) | N/A | N/A |  | DEV, SE, OPS | DG Office MMD